## Vision burndown
Vision burndown plan
Starting items | 30 |  | Plan balance | Balanced
Unweighted backlog items. Planned line only; actual remaining is blank until each sprint is reviewed.
Sprint | Planned items | Planned remaining | Actual remaining | Milestone
Start | 0 | 30 |  | Baseline plan
S1 | 4 | 26
S2 | 4 | 22
S3 | 4 | 18
S4 | 5 | 13
S5 | 5 | 8 |  | 30 ms MVP gate
S6 | 3 | 5
S7 | 3 | 2 |  | 10 ms final goal
S8 | 2 | 0 |  | Final validation
Update planned counts when sprint assignments change. Enter actual remaining only after a sprint review.