## Project backlog
Full ML guitar pedal vision
Vision items | 30 |  | MVP items | 23 |  | Final items | 7
Planning baseline. Owner and status are intentionally blank; no completion is implied.
ID | Horizon | Workstream | Outcome | Acceptance evidence | Depends on | Owner | Status
P01 | MVP | Platform | Choose Raspberry Pi platform and OS image | Pi boots repeatably with versioned OS and audio prerequisites recorded
P02 | MVP | Audio hardware | Select a guitar-capable audio interface | Capture and playback work at the target sample rate on the Pi | P01
P03 | MVP | Audio engine | Stream guitar input through effect output | Continuous live path runs with recovery counts and no unintended stops | P02
P04 | MVP | Audio engine | Switch between clean and effect modes | Switching is audible, controllable, and free of switching clicks | P03
P06 | MVP | ML pitch | Collect and label clean guitar recordings | Dataset covers chosen strings, frets, and pickups with documented labels | P02
P07 | MVP | ML pitch | Train and evaluate pitch classifier | Training run, holdout results, and model artifact are reproducible | P06
P08 | MVP | ML pitch | Run pitch inference on the Pi | Live input produces note estimates with measured inference timing | P03, P07
P09 | MVP | Effects | Provide several usable effects | Overdrive plus at least two distinct effects are selectable and adjustable | P03
P11 | MVP | Physical control | Add reliable footswitch control | Presses change modes or presets without duplicate triggers | P04
P12 | MVP | Electronics | Design dedicated GPIO interface circuit | Schematic covers switch inputs, protection, connectors, and safe Pi voltage levels | P01, P11
P14 | MVP | Display | Select and connect a Pi screen | Screen renders the application at intended resolution and power budget | P01
P15 | MVP | UI | Design a clear pedal interface | UI shows effect, preset, bypass state, levels, and key parameters | P14
P10 | MVP | Effects | Save and recall presets | Preset changes restore effect type and parameter values reliably | P09
P13 | MVP | Electronics | Build and test GPIO interface PCB | Assembled circuit passes continuity, input, and electrical safety checks | P12
P16 | MVP | UI | Control effects from the screen | Touch or alternate input changes parameters with visible feedback | P10, P15
P17 | MVP | Integration | Integrate audio, screen, and physical controls | All controls operate while audio continues without interruption | P03, P11, P13, P16
P18 | MVP | Enclosure | Prototype 3D-printed case | Pi, interface, screen, PCB, jacks, and controls fit and remain accessible | P02, P13, P14
P05 | MVP | Performance | Meet immediate 30 ms latency target | Defined product latency test records result below 30 ms on target hardware | P17
P19 | MVP | Power | Provide safe power and shutdown behavior | Power path and shutdown process avoid corruption and unsafe GPIO states | P17
P20 | MVP | Reliability | Start and recover the pedal automatically | Service starts after boot and surfaces failures without silent audio loss | P17
P21 | MVP | Audio quality | Check noise and signal integrity | Input/output noise, clipping, and level tests are documented on hardware | P17
P22 | MVP | Audio safety | Set safe output and bypass levels | Default gains and bypass transition avoid sudden loud output | P04, P17
P23 | MVP | User testing | Run alpha player sessions | Players complete core tasks; findings and fixes are recorded | P05, P18, P20
P25 | Final | ML effects | Deploy a trained ML audio effect | A trained timbre effect runs on-device and is selectable in the chain | P07, P09, P17
P26 | Final | Effects | Support multi-effect chains | Players can route and adjust multiple effects in one preset | P10, P25
P24 | Final | Performance | Meet long-term 10 ms latency goal | Same defined product latency test records result below 10 ms on target hardware | P05, P26
P27 | Final | Release | Document update and recovery process | Software and model updates can be applied and rolled back | P20, P25
P28 | Final | Build | Finalize bill of materials and assembly | Parts, enclosure files, circuit revision, and assembly steps are reproducible | P13, P18
P29 | Final | Validation | Complete final player and hardware validation | Endurance, usability, audio quality, and latency checks pass | P24, P26, P27, P28
P30 | Final | Documentation | Publish final user and service guides | Setup, operation, maintenance, and troubleshooting match shipped build | P29
MVP target: product latency below 30 ms. Final goal: below 10 ms. Define and record the same hardware test for both.