## Sprint backlog
Vision sprint plan
Assigned items | 30 |  | Sprints | 8
Sequencing proposal. Sprint dates, owners, and completion status remain open for the team.
Sprint | Goal | Project ID | Planned deliverable | Exit evidence | Owner | Status
S1 | Establish Pi audio foundation | P01 | Choose Raspberry Pi platform and OS image | Pi boots repeatably with versioned OS and audio prerequisites recorded
S1 | Establish Pi audio foundation | P02 | Select a guitar-capable audio interface | Capture and playback work at the target sample rate on the Pi
S1 | Establish Pi audio foundation | P03 | Stream guitar input through effect output | Continuous live path runs with recovery counts and no unintended stops
S1 | Establish Pi audio foundation | P04 | Switch between clean and effect modes | Switching is audible, controllable, and free of switching clicks
S2 | Prove pitch and multiple effects | P06 | Collect and label clean guitar recordings | Dataset covers chosen strings, frets, and pickups with documented labels
S2 | Prove pitch and multiple effects | P07 | Train and evaluate pitch classifier | Training run, holdout results, and model artifact are reproducible
S2 | Prove pitch and multiple effects | P08 | Run pitch inference on the Pi | Live input produces note estimates with measured inference timing
S2 | Prove pitch and multiple effects | P09 | Provide several usable effects | Overdrive plus at least two distinct effects are selectable and adjustable
S3 | Design physical control and screen UI | P11 | Add reliable footswitch control | Presses change modes or presets without duplicate triggers
S3 | Design physical control and screen UI | P12 | Design dedicated GPIO interface circuit | Schematic covers switch inputs, protection, connectors, and safe Pi voltage levels
S3 | Design physical control and screen UI | P14 | Select and connect a Pi screen | Screen renders the application at intended resolution and power budget
S3 | Design physical control and screen UI | P15 | Design a clear pedal interface | UI shows effect, preset, bypass state, levels, and key parameters
S4 | Integrate controls and case prototype | P10 | Save and recall presets | Preset changes restore effect type and parameter values reliably
S4 | Integrate controls and case prototype | P13 | Build and test GPIO interface PCB | Assembled circuit passes continuity, input, and electrical safety checks
S4 | Integrate controls and case prototype | P16 | Control effects from the screen | Touch or alternate input changes parameters with visible feedback
S4 | Integrate controls and case prototype | P17 | Integrate audio, screen, and physical controls | All controls operate while audio continues without interruption
S4 | Integrate controls and case prototype | P18 | Prototype 3D-printed case | Pi, interface, screen, PCB, jacks, and controls fit and remain accessible
S5 | Pass the minimum acceptable build | P05 | Meet immediate 30 ms latency target | Defined product latency test records result below 30 ms on target hardware
S5 | Pass the minimum acceptable build | P19 | Provide safe power and shutdown behavior | Power path and shutdown process avoid corruption and unsafe GPIO states
S5 | Pass the minimum acceptable build | P20 | Start and recover the pedal automatically | Service starts after boot and surfaces failures without silent audio loss
S5 | Pass the minimum acceptable build | P21 | Check noise and signal integrity | Input/output noise, clipping, and level tests are documented on hardware
S5 | Pass the minimum acceptable build | P22 | Set safe output and bypass levels | Default gains and bypass transition avoid sudden loud output
S6 | Test alpha and expand effects | P23 | Run alpha player sessions | Players complete core tasks; findings and fixes are recorded
S6 | Test alpha and expand effects | P25 | Deploy a trained ML audio effect | A trained timbre effect runs on-device and is selectable in the chain
S6 | Test alpha and expand effects | P26 | Support multi-effect chains | Players can route and adjust multiple effects in one preset
S7 | Optimize and prepare repeatable build | P24 | Meet long-term 10 ms latency goal | Same defined product latency test records result below 10 ms on target hardware
S7 | Optimize and prepare repeatable build | P27 | Document update and recovery process | Software and model updates can be applied and rolled back
S7 | Optimize and prepare repeatable build | P28 | Finalize bill of materials and assembly | Parts, enclosure files, circuit revision, and assembly steps are reproducible
S8 | Validate the full product | P29 | Complete final player and hardware validation | Endurance, usability, audio quality, and latency checks pass
S8 | Validate the full product | P30 | Publish final user and service guides | Setup, operation, maintenance, and troubleshooting match shipped build
S5 gates the 30 ms minimum acceptable build; S7 targets the 10 ms long-term goal. Neither target is marked achieved.