## Vision burndown
ESOF-aligned burndown plan
Starting items | 30 |  | Plan balance | Balanced
Unweighted items. ESOF dates anchor phases; the 10 ms goal is undated. Actual remaining stays blank.
Phase | ESOF due | Planned items | Planned remaining | Actual remaining | Checkpoint
Start |  | 0 | 30 |  | Baseline plan
S1 | 2026-10-16T12:00:00.000Z | 4 | 26 |  | Beta demo, Portfolio Draft
S2 | 2026-10-23T12:00:00.000Z | 7 | 19 |  | Playwright Exercise
S3 | 2026-10-30T12:00:00.000Z | 6 | 13 |  | FCR Demo, Docs
S4 | 2026-11-06T12:00:00.000Z | 4 | 9 |  | User Testing
S5 | 2026-11-13T12:00:00.000Z | 3 | 6 |  | RC Demo, Final Artifacts
S6 | 2026-11-20T12:00:00.000Z | 2 | 4 |  | Post Mortem
S7 | 2026-12-04T12:00:00.000Z | 3 | 1 |  | 30 ms minimum gate
S8 | 2026-12-11T12:00:00.000Z | 0 | 1 |  | Presentations
S9 | 2026-12-17T12:00:00.000Z | 0 | 1 |  | Demo Video, Portfolio
S10 |  | 1 | 0 |  | 10 ms long-term goal
Update planned counts if project assignments change. S8-S9 are course milestones with no planned product item closure.