## ESOF timeline
ESOF 423 deadlines
Dated todo items | 12 |  | Long-term goal | Date TBD
Source: local todo command, ESOF 423 entries, read 2026-10-09. Product assignments are proposed.
Due date | ESOF todo item | Kind | Roadmap phase | Planning use
2026-10-16T12:00:00.000Z | Beta demo, Portfolio Draft | Project checkpoint | S1 | Demonstrate the current baseline
2026-10-23T12:00:00.000Z | Playwright Exercise | Course task | S2 | Keep separate from product acceptance
2026-10-30T12:00:00.000Z | FCR Demo, Docs | Project checkpoint | S3 | Show integrated alpha and documentation
2026-11-06T12:00:00.000Z | User Testing | Project checkpoint | S4 | Record player feedback
2026-11-13T12:00:00.000Z | RC Demo, Final Artifacts | Project checkpoint | S5 | Show release candidate and artifacts
2026-11-20T12:00:00.000Z | Post Mortem | Course task | S6 | Record retrospective and remaining risks
2026-12-04T12:00:00.000Z | Production Readiness | Project checkpoint | S7 | Check the 30 ms minimum build
2026-12-07T12:00:00.000Z | Attend final presentations | Course event | S8 | No product completion implied
2026-12-09T12:00:00.000Z | Attend final presentations | Course event | S8 | No product completion implied
2026-12-11T12:00:00.000Z | Presentations | Course event | S8 | Present the build
2026-12-11T12:00:00.000Z | Attend final presentations | Course event | S8 | No product completion implied
2026-12-17T12:00:00.000Z | Demo Video, Portfolio | Project closeout | S9 | Publish demo and portfolio materials
The 10 ms product goal follows the ESOF deadlines; no due date is supplied by todo.

## Sprint backlog
Dated product work plan
Assigned items | 30 |  | Dated phases | 9
ESOF dates are fixed checkpoints; project item placement is proposed. Blank owner and status do not mean complete.
Phase | ESOF due | ESOF checkpoint | Goal | Project ID | Planned deliverable | Exit evidence | Owner | Status
S1 | 2026-10-16T12:00:00.000Z | Beta demo, Portfolio Draft | Beta demo baseline | P01 | Choose Raspberry Pi platform and OS image | Pi boots repeatably with versioned OS and audio prerequisites recorded
S1 | 2026-10-16T12:00:00.000Z | Beta demo, Portfolio Draft | Beta demo baseline | P02 | Select a guitar-capable audio interface | Capture and playback work at the target sample rate on the Pi
S1 | 2026-10-16T12:00:00.000Z | Beta demo, Portfolio Draft | Beta demo baseline | P06 | Collect and label clean guitar recordings | Dataset covers chosen strings, frets, and pickups with documented labels
S1 | 2026-10-16T12:00:00.000Z | Beta demo, Portfolio Draft | Beta demo baseline | P07 | Train and evaluate pitch classifier | Training run, holdout results, and model artifact are reproducible
S2 | 2026-10-23T12:00:00.000Z | Playwright Exercise | Pi hardware and effect path | P03 | Stream guitar input through effect output | Continuous live path runs with recovery counts and no unintended stops
S2 | 2026-10-23T12:00:00.000Z | Playwright Exercise | Pi hardware and effect path | P04 | Switch between clean and effect modes | Switching is audible, controllable, and free of switching clicks
S2 | 2026-10-23T12:00:00.000Z | Playwright Exercise | Pi hardware and effect path | P08 | Run pitch inference on the Pi | Live input produces note estimates with measured inference timing
S2 | 2026-10-23T12:00:00.000Z | Playwright Exercise | Pi hardware and effect path | P09 | Provide several usable effects | Overdrive plus at least two distinct effects are selectable and adjustable
S2 | 2026-10-23T12:00:00.000Z | Playwright Exercise | Pi hardware and effect path | P11 | Add reliable footswitch control | Presses change modes or presets without duplicate triggers
S2 | 2026-10-23T12:00:00.000Z | Playwright Exercise | Pi hardware and effect path | P12 | Design dedicated GPIO interface circuit | Schematic covers switch inputs, protection, connectors, and safe Pi voltage levels
S2 | 2026-10-23T12:00:00.000Z | Playwright Exercise | Pi hardware and effect path | P14 | Select and connect a Pi screen | Screen renders the application at intended resolution and power budget
S3 | 2026-10-30T12:00:00.000Z | FCR Demo, Docs | Integrated alpha and docs | P10 | Save and recall presets | Preset changes restore effect type and parameter values reliably
S3 | 2026-10-30T12:00:00.000Z | FCR Demo, Docs | Integrated alpha and docs | P13 | Build and test GPIO interface PCB | Assembled circuit passes continuity, input, and electrical safety checks
S3 | 2026-10-30T12:00:00.000Z | FCR Demo, Docs | Integrated alpha and docs | P15 | Design a clear pedal interface | UI shows effect, preset, bypass state, levels, and key parameters
S3 | 2026-10-30T12:00:00.000Z | FCR Demo, Docs | Integrated alpha and docs | P16 | Control effects from the screen | Touch or alternate input changes parameters with visible feedback
S3 | 2026-10-30T12:00:00.000Z | FCR Demo, Docs | Integrated alpha and docs | P17 | Integrate audio, screen, and physical controls | All controls operate while audio continues without interruption
S3 | 2026-10-30T12:00:00.000Z | FCR Demo, Docs | Integrated alpha and docs | P20 | Start and recover the pedal automatically | Service starts after boot and surfaces failures without silent audio loss
S4 | 2026-11-06T12:00:00.000Z | User Testing | Player feedback | P18 | Prototype 3D-printed case | Pi, interface, screen, PCB, jacks, and controls fit and remain accessible
S4 | 2026-11-06T12:00:00.000Z | User Testing | Player feedback | P21 | Check noise and signal integrity | Input/output noise, clipping, and level tests are documented on hardware
S4 | 2026-11-06T12:00:00.000Z | User Testing | Player feedback | P22 | Set safe output and bypass levels | Default gains and bypass transition avoid sudden loud output
S4 | 2026-11-06T12:00:00.000Z | User Testing | Player feedback | P23 | Run alpha player sessions | Players complete core tasks; findings and fixes are recorded
S5 | 2026-11-13T12:00:00.000Z | RC Demo, Final Artifacts | Release candidate effects | P19 | Provide safe power and shutdown behavior | Power path and shutdown process avoid corruption and unsafe GPIO states
S5 | 2026-11-13T12:00:00.000Z | RC Demo, Final Artifacts | Release candidate effects | P25 | Deploy a trained ML audio effect | A trained timbre effect runs on-device and is selectable in the chain
S5 | 2026-11-13T12:00:00.000Z | RC Demo, Final Artifacts | Release candidate effects | P26 | Support multi-effect chains | Players can route and adjust multiple effects in one preset
S6 | 2026-11-20T12:00:00.000Z | Post Mortem | Build review and retrospective | P27 | Document update and recovery process | Software and model updates can be applied and rolled back
S6 | 2026-11-20T12:00:00.000Z | Post Mortem | Build review and retrospective | P28 | Finalize bill of materials and assembly | Parts, enclosure files, circuit revision, and assembly steps are reproducible
S7 | 2026-12-04T12:00:00.000Z | Production Readiness | Minimum acceptable production build | P05 | Meet immediate 30 ms latency target | Defined product latency test records result below 30 ms on target hardware
S7 | 2026-12-04T12:00:00.000Z | Production Readiness | Minimum acceptable production build | P29 | Complete final player and hardware validation | Endurance, usability, audio quality, and 30 ms latency checks pass
S7 | 2026-12-04T12:00:00.000Z | Production Readiness | Minimum acceptable production build | P30 | Publish final user and service guides | Setup, operation, maintenance, and troubleshooting match shipped build
S10 |  | After ESOF timeline; date TBD | Long-term latency optimization | P24 | Meet long-term 10 ms latency goal | Same defined product latency test records result below 10 ms on target hardware
The 30 ms gate is aligned to Production Readiness on 2026-12-04. The 10 ms goal is an undated S10 phase after ESOF.